## Slide 1: Transforming Grant Management: Delivering Sustainable Cross-Department Change at Scale
Gem Brown, Head of Grant Management
University of Oxford
A practical case study in reducing risk, improving resilience and scaling support without losing local relationships

## Slide 2: Context
Nuffield Department of Medicine (NDM):
~3,500 staff
200+ Principal Investigators
Research portfolio worth ~£1.2bn
>850 active projects
Department of Paediatrics (DoP):
~400 staff
50+ Principal Investigators
Research portfolio worth ~£320m
>250 active projects

## Slide 3: The case for change
In 2020:
Increased value, volume, and complexity
Support was highly fragmented across local teams
Struggled to maintain efficient and effective levels of service
Sponsor audits highlighted areas for improvement
Recruitment gaps and staff attrition
Development and progression routes were limited
Increasing financial pressures on HEIs

## Slide 4: What was at risk?
People
Recruitment, retention, competence and wellbeing
Mitigation:
Design progression routes; use skills deliberately; provide training and peer support
Compliance
Audit exposure, funder terms and reputational consequences
Mitigation:
Standardise processes; clarify accountability and improve evidence management
Financial
Pressure on overheads, funding mix and portfolio management
Mitigation:
Improve visibility of activity; support more strategic choices and right-first-time practice
Culture
Academic confidence, local habits and trust in professional services
Mitigation:
Consult widely; retain local decision routes and train all stakeholder groups

## Slide 5: The solution
A fully consolidated team
Build an agile function
A central hub, with hot desking in academic Units
Career development opportunities
Structured training provision
Exploration and implementation of digital solutions
Unify systems and processes
To provide an effective, efficient and robust support infrastructure that will transform grant management in NDM

## Slide 6: How implementation was de-risked
Consult
Academics, business managers, grants staff were engaged early.
Support
Individual consultation, HR support, training and clear communications.
Phase
Transitional period, staged onboarding and regular operational reviews.
Embed
Governance, SOPs, portfolio reviews and escalation routes.
Legitimacy
Support
Pacing
Habit

## Slide 7: What changed in practice?
Common roles
Consistent job descriptions and clearer responsibilities
Shared ways of working
SOPs, document management and systems access
Portfolio rhythm
Regular reviews, standard reports and clearer escalation
Continuous learning
Training, feedback loops and lessons learned

## Slide 8: Scaling the model: Department of Paediatrics
September 2024
Initial trial commences with DoP non-clinical portfolio only
May 2025
Full portfolio taken on by NDM for one-year trial
May 2026
Permanent embedded shared- function model agreed
June 2024
Vacancies in DoP create a live opportunity to explore shared support
March 2025
Further vacancies create a need to broaden scope

## Slide 9: What was harder than expected?
Local practice varied more than expected
Escalation routes mattered
A shared service still needs clear local decision-making and prioritisation
Trust took repeated explanation
Stakeholders needed to hear the “why” more than once, especially during transition
Professional services integration needed focus
Alignment with other professional services structures was as important as grants team design
Historical processes needed mapping before standardisation could stick

## Slide 10: Evidence of value
Resilience
  Shared capacity improved workload balancing and reduced dependency on single roles
Consistency
  Standardised processes improved service quality and reduced variation
Efficiency
  Cost-neutral shared model created a scalable route for future support, without rebuilding from scratch
Compliance
Sustainability
  Better oversight, audit readiness and coordination across collaborative projects
People
  Progression, peer support and shared learning supported retention
  Repeated practice and unified systems improved speed

## Slide 11: Key messages
Start with the risk
Name the operational and compliance exposure before proposing structure
Design for people
Standardise before you scale
  Central resilience works best when local decision routes remain clear
Trial with exit routes
Keep local nuance
  Proof-of-concept pilots lower fear and create usable evidence
  Shared services need common processes, not just shared reporting lines
  Build progression, peer support and wellbeing into the operating model
Sustainable transformation happens when efficiency, resilience and staff development are designed together